## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Dependency | Status
sprint 1 | sprint 1 | us-001 | Desgine the multi_agent system (MAS)Architecture Diagram | MUST HAVE | none | Brunda | 3- Completed
sprint 1 | sprint 1 | us-002 | Explain the framework and MAS workflow with justification | MUST HAVE | Architecture diagram | sailaja | 3- Completed
sprint 1 | sprint 1 | us-003 | Develop web search agent to retrive market trends and compitator data using tavilyApi | MUST HAVE | Frame work | Swathi | 3- Completed
sprint 1 | sprint 1 | us-004 | Create startup idea submission frontend (HTML/CSS/JS) | MUST HAVE | web search agent | Shirisha | 3- Completed
sprint 1 | sprint 1 | us-005 | Integrate frontend with web search agent | SHOULD HAVE | frontend+backend | Swathi | 3- Completed
sprint 1 | sprint 1 | us-006 | Test web search agent with sample startup idea | SHOULD HAVE | Integration | Team | 3- Completed
sprint 1 | sprint 1 | us-007 | prepare documentation | COULD HAVE | All Tasks | sailaja | 3- Completed
sprint 1 | sprint 1 | us-008 | Git hub repository | COULD HAVE | All Tasks | Shirisha | 3- Completed
sprint 2 | sprint 2 | us-009 | Develop comparison agent for startup idea validation | MUST HAVE | Competitive analysis agent | Brunda | 3- Completed
sprint 2 | sprint 2 | us-010 | Develop agent orchestration for multi-agent workflow | MUST HAVE | All agents | Sailaja | 3- Completed
sprint 2 | sprint 2 | us-011 | Develop market and customer segmentation agent | MUST HAVE | Web search agent | Shirisha | 3- Completed
sprint 2 | sprint 2 | us-012 | Develop competitive analysis agent | MUST HAVE | Web search agent | Priya | 3- Completed
sprint 2 | sprint 2 | us-013 | Perform integration testing and validate application | SHOULD HAVE | All agents | Swathi | 3- Completed
sprint 3 | sprint 3 | us-014 | Develop SWOT Analysis Agent to generate structured strengths, weaknesses, opportunities and threats using LLM reasoning | MUST HAVE | Market and Competitive Analysis Agents | Brunda | 3- Completed
sprint 3 | sprint 3 | us-015 | Develop Risk Analysis Agent to identify and evaluate key risks associated with a startup idea | MUST HAVE | SWOT Analysis Agent | Brunda | 3- Completed
sprint 3 | sprint 3 | us-016 | Develop MVP Feature Recommendation Agent to prioritize core startup features based on market fit and resource constraints | MUST HAVE | Market and Customer Segmentation Agent | Shirisha | 3- Completed
sprint 3 | sprint 3 | us-017 | Develop Go-To-Market Strategy generation for positioning, channels and early customer acquisition | MUST HAVE | Competitive Analysis and Market Analysis Agents | Priya | 3- Completed
sprint 3 | sprint 3 | us-018 | Develop conversational startup advisor for follow-up queries and deeper exploration of validation results | MUST HAVE | Agent Orchestration | sailaja | 3- Completed
sprint 3 | sprint 3 | us-019 | Perform integration testing of newly developed agents with existing validation workflow | SHOULD HAVE | All Sprint 3 Agents | Swathi | 3- Completed
sprint 4 | sprint 4 | us-020 | Develop Startup Validation Report Generation Agent to compile outputs from all agents into a structured report | MUST HAVE | All Validation Agents | Sailaja | 3- Completed
sprint 4 | sprint 4 | us-021 | Implement downloadable PDF generation for the complete startup validation report | MUST HAVE | Report Generation Agent | sailaja | 3- Completed
sprint 4 | sprint 4 | us-022 | Conduct end-to-end testing across all agents, web search integration and report generation workflow | MUST HAVE | Complete Agent Workflow | Swathi | 3- Completed
sprint 4 | sprint 4 | us-023 | Optimize web search query design and improve relevance of retrieved market and competitor information | SHOULD HAVE | Web Search Agent | Swathi | 3- Completed
sprint 4 | sprint 4 | us-024 | Optimize prompt engineering, agent reasoning quality and output accuracy across validation agents | SHOULD HAVE | All AI Agents | Brunda | 3- Completed
sprint 4 | sprint 4 | us-025 | Validate startup validation outputs using sample ideas from different domains | SHOULD HAVE | Complete Validation Workflow | Priya | 3- Completed
sprint 4 | sprint 4 | us-026 | Prepare technical documentation, final project report and demonstration materials | MUST HAVE | Completed System | sailaja | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 170 | 17 | 17 | 19 | 18 | 21 | 17 | 13 | 13 | 11 | 9 | 5 | 5 | 3 | 2
SPRINT 1 BACKLOG
us-001 | 1 | Design the overall architecture for the multi-agent startup validation system | 2026-07-06 | 2026-07-07 | Brunda | Architecture | completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
us-002 | 2 | Set up the AI agent framework and define the initial agent workflow | 2026-07-06 | 2026-07-08 | Sailaja | coding | completed | 8 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
us-003 | 3 | Develop web search agent to retrive market trends and compitator data using tavilyApi | 2026-07-06 | 2026-07-07 | Swathi | coding | completed | 4 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
us-004 | 4 | Develop the initial frontend interface for submitting startup ideas | 2026-07-08 | 2026-07-11 | Shirisha | coding | completed | 8 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
us-005 | 5 | integrate frontend with web serach agent | 2026-07-11 | 2026-07-11 | Swathi | Integration | completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
us-006 | 6 | Test the web search agent with sample startup ideas and validate retrieved information | 2026-07-11 | 2026-07-13 | Team | testing | completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
us-007 | 7 | Prepare initial technical documentation for the project architecture and workflow | 2026-07-12 | 2026-07-14 | Sailaja | documentation | completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
us-008 | 8 | Create and organize the project repository and initial project structure | 2026-07-06 | 2026-07-14 | Shirisha | repository | completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
us-009 | 1 | Develop Comparison Agent | 15-Jul-2026 | 27-Jul-2026 | Brunda | coding | completed | 10 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
us-010 | 2 | Develop Agent Orchestration | 15-Jul-2026 | 27-Jul-2026 | Sailaja | coding | completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
us-011 | 3 | Develop Market & Customer Segmentation Agent | 15-Jul-2026 | 26-Jul-2026 | Shirisha | coding | completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
us-012 | 4 | Develop Competitive Analysis Agent | 15-Jul-2026 | 26-Jul-2026 | Priya | coding | completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
us-013 | 5 | Integration Testing and Validation | 24-Jul-2026 | 27-Jul-2026 | Swathi | testing | completed | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
us-014 | 1 | Develop SWOT Analysis Agent | 2026-07-28 | 2026-08-03 | Brunda | coding | completed | 6 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
us-015 | 2 | Develop Risk Analysis Agent | 2026-07-31 | 2026-08-05 | Brunda | coding | completed | 5 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
us-016 | 3 | Develop MVP Feature Recommendation Agent | 2026-07-28 | 2026-08-05 | Shirisha | coding | completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
us-017 | 4 | Develop Go-To-Market Strategy Agent | 2026-07-29 | 2026-08-05 | Priya | coding | completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
us-018 | 5 | Develop Conversational Startup Advisor | 2026-08-03 | 2026-08-09 | Sailaja | coding | completed | 8 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
us-019 | 6 | Integrate and Test Sprint 3 Agents | 2026-08-06 | 2026-08-10 | Swathi | testing | completed | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
us-020 | 1 | Develop Startup Validation Report Generation Agent | 2026-08-11 | 2026-08-17 | Sailaja | coding | completed | 6 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
us-021 | 2 | Implement Downloadable PDF Report Generation | 2026-08-14 | 2026-08-20 | Sailaja | coding | completed | 5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
us-022 | 3 | Conduct End-to-End Testing Across Complete Workflow | 2026-08-17 | 2026-08-24 | Swathi | testing | completed | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
us-023 | 4 | Optimize Web Search Queries and Retrieval Relevance | 2026-08-11 | 2026-08-18 | Swathi | coding | completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
us-024 | 5 | Optimize Prompt Engineering and Agent Output Accuracy | 2026-08-12 | 2026-08-20 | Brunda | coding | completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
us-025 | 6 | Validate Outputs Across Different Startup Domains | 2026-08-18 | 2026-08-22 | Priya | testing | completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
us-026 | 7 | Prepare Technical Documentation, Project Report and Final Demo | 2026-08-17 | 2026-08-24 | Sailaja | documentation | completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
sprint 1 | Day2 | Lack of understanding of project requirements | Discussed with team members and mentor to clarify requirements
sprint 1 | Day3 | Difficulty of understanding project architecture | Studied the architecture diagram and team documentation
sprint 1 | Day4 | Git hud setup and integration issue | configured Github cloned the repo and tested the setup
sprint 1 | Day5 | Limited Knowledge of APIs | Explore API documentation and tested sample API requestes
sprint 1 | Day8 | Difficulty writing backend code | worked with teammates and reffered to project examples
sprint 1 | Day10 | API integration errors | fixed requests issues
sprint 1 | Day13 | Code testing issues | Tested web search agent and fixed bugs
sprint 1 | Day14 | Final integration and review | completed implementation,commite code,and submited milestone1
sprint 2 | Day 2 | Comparison agent API was not returning expected output. | Verified API using Swagger and fixed OpenRouter configuration.
sprint 2 | Day 5 | Integration of all agents was pending. | Completed individual modules and shared code for integration.
sprint 2 | Day 8 | Outputs were not visible in UI after integration. | Verified APIs and coordinated with orchestration module.
sprint 2 | Day 11 | Common environment setup required for testing. | Shared updated .env file and tested locally.
sprint 2 | Day 14 | Final integration and deployment preparation. | Completed testing, fixed remaining issues and prepared milestone submission.
sprint 3 | Day 2 | Difficulty structuring SWOT analysis outputs | Reviewed requirements and refined the SWOT output format and prompts
sprint 3 | Day 4 | Risk analysis required clear prioritization of startup risks | Added risk categories and severity-based evaluation to the agent
sprint 3 | Day 6 | MVP recommendations were too generic | Added market-fit and resource constraints to the recommendation criteria
sprint 3 | Day 8 | GTM strategy required better alignment with market and competitor findings | Refined strategy prompts using market and competitor insights
sprint 3 | Day 11 | Conversational advisor required context from previous agent outputs | Updated orchestration to pass relevant validation results as context
sprint 3 | Day 14 | Integration issues occurred while connecting the new agents | Performed integration testing and fixed workflow and API issues
sprint 4 | Day 2 | Report generation required outputs from multiple agents in a consistent structure | Standardized the output format across validation agents
sprint 4 | Day 4 | Combining multiple agent outputs into a final report was challenging | Implemented the report generation workflow
sprint 4 | Day 6 | PDF generation required proper formatting of validation results | Integrated and tested downloadable PDF report generation
sprint 4 | Day 8 | Some web search results were not sufficiently relevant | Refined search query design and retrieval parameters
sprint 4 | Day 10 | Some agent responses required improvement in accuracy and consistency | Improved prompts and validated outputs against sample startup ideas
sprint 4 | Day 12 | Different startup domains produced varying validation results | Tested the system with startup ideas from multiple domains
sprint 4 | Day 14 | Final testing and documentation were pending | Completed E2E testing, fixed remaining issues and finalized documentation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | sprint 1 | 2026-07-06 | 2026-07-14 | Brunda | Start documenting architecture decisions clearly | Stop making architecture decisions informally | Continue contributing to system architecture | Created and documented the multi-agent system architecture
2 | sprint 1 | 2026-07-06 | 2026-07-14 | Sailaja | Start defining the framework workflow early | Stop developing without a clear agent flow | Continue framework development | Explained the framework and multi-agent workflow
3 | sprint 1 | 2026-07-06 | 2026-07-14 | Swathi | Start validating APIs with sample requests | Stop relying on assumptions about API behavior | Continue web search development | Developed and tested the Tavily web search agent
4 | sprint 1 | 2026-07-06 | 2026-07-14 | Shirisha | Start planning the frontend flow before implementation | Stop making UI changes without a defined structure | Continue frontend development | Created the startup idea submission interface
5 | sprint 1 | 2026-07-06 | 2026-07-14 | Swathi | Start testing integration after each major change | Stop postponing integration testing | Continue integration work | Integrated the frontend with the web search agent
6 | sprint 1 | 2026-07-06 | 2026-07-14 | Team | Start using representative startup ideas for testing | Stop testing only individual components | Continue collaborative testing | Tested the web search agent using sample startup ideas
7 | sprint 1 | 2026-07-06 | 2026-07-14 | Sailaja | Start maintaining documentation throughout development | Stop leaving documentation until the end | Continue technical documentation | Prepared project documentation alongside development
8 | sprint 1 | 2026-07-06 | 2026-07-14 | Shirisha | Start maintaining a common repository structure | Stop keeping project files locally | Continue project organization | Created and maintained the GitHub repository
9 | sprint 2 | 2026-07-15 | 2026-07-27 | Brunda | Start comparing startup ideas using consistent criteria | Stop relying on individual comparison factors | Continue analytical development | Developed the comparison agent and standardized comparison criteria
10 | sprint 2 | 2026-07-15 | 2026-07-27 | Sailaja | Start tracking dependencies between agents | Stop treating agents as independent modules | Continue orchestration development | Developed the multi-agent orchestration workflow
11 | sprint 2 | 2026-07-15 | 2026-07-27 | Shirisha | Start incorporating customer segments into validation | Stop keeping market analysis too generic | Continue market and customer analysis | Developed the market and customer segmentation agent
12 | sprint 2 | 2026-07-15 | 2026-07-27 | Priya | Start connecting competitor insights to startup positioning | Stop treating competitors as isolated data points | Continue competitive analysis | Developed the competitive analysis agent
13 | sprint 2 | 2026-07-15 | 2026-07-27 | Swathi | Start performing integration tests throughout development | Stop waiting until the final stage for testing | Continue integration and testing | Completed integration testing and validated the application
14 | sprint 3 | 2026-07-28 | 2026-08-10 | Brunda | Start validating analytical outputs systematically | Stop relying on unstructured prompts | Continue analytical agent development | Structured and validated SWOT analysis outputs
15 | sprint 3 | 2026-07-28 | 2026-08-10 | Brunda | Start categorizing risks based on severity and impact | Stop treating all risks equally | Continue analytical evaluation | Added structured risk categorization and prioritization
16 | sprint 3 | 2026-07-28 | 2026-08-10 | Shirisha | Start incorporating resource constraints into recommendations | Stop generating generic feature suggestions | Continue market and customer analysis | Added market-fit and resource criteria to MVP recommendations
17 | sprint 3 | 2026-07-28 | 2026-08-10 | Priya | Start connecting competitive insights with strategy | Stop using generic strategy assumptions | Continue competitive analysis | Improved GTM strategy using market and competitor insights
18 | sprint 3 | 2026-07-28 | 2026-08-10 | Sailaja | Start maintaining context across agent conversations | Stop treating agent outputs independently | Continue orchestration development | Improved context passing for the conversational advisor
19 | sprint 3 | 2026-07-28 | 2026-08-10 | Swathi | Start integration testing earlier | Stop waiting until final integration | Continue integration and API testing | Performed iterative integration testing and resolved issues
20 | sprint 4 | 2026-08-11 | 2026-08-24 | Sailaja | Start standardizing agent outputs for final reporting | Stop passing inconsistent outputs to the report generator | Continue orchestration development | Standardized agent outputs and implemented the report workflow
21 | sprint 4 | 2026-08-11 | 2026-08-24 | Sailaja | Start validating report formatting during development | Stop leaving document formatting until the end | Continue documentation work | Tested PDF generation and improved report formatting
22 | sprint 4 | 2026-08-11 | 2026-08-24 | Swathi | Start optimizing search queries systematically | Stop using broad search queries | Continue web search and integration testing | Improved search queries and retrieval relevance
23 | sprint 4 | 2026-08-11 | 2026-08-24 | Brunda | Start systematically evaluating prompt quality | Stop using unoptimized prompts | Continue analytical validation | Refined prompts and improved agent output accuracy
24 | sprint 4 | 2026-08-11 | 2026-08-24 | Priya | Start testing outputs across multiple startup domains | Stop validating with a single startup idea | Continue competitive and strategy analysis | Validated outputs using different startup scenarios
25 | sprint 4 | 2026-08-11 | 2026-08-24 | Swathi | Start performing E2E testing throughout integration | Stop treating modules as isolated components | Continue systematic testing | Completed E2E testing and resolved workflow issues
26 | sprint 4 | 2026-08-11 | 2026-08-24 | Sailaja | Start organizing final documentation alongside development | Stop postponing final documentation | Continue project documentation and orchestration | Completed technical documentation, final report and demo preparation